## Sprint 1
Sprint 1
Name |  | Authentication sprint |  |  |  | 0
Goal |  | add all functionalities of authentication |  | Duration | 5 working days
Process improvement |  | improve sprint reporting |  | Things | 8 things
Start Date |  | 2025-08-03 |  | Story Points | 24 points
End Date |  | 2025-08-08 |  |  |  | days left
Sprint Metrics
Things Planned |  | 8 | Key Achievements | Completed 8 user stories (24 story points) focused on authentication flows for patients and doctors (register, login, remember password, logout). Established a unified authentication logic reusable across roles (patient/doctor).
Points Planned |  | 24
Things done: |  | 8
Things left: |  | 0 | Performance Summary | IMTA-2557 we should have kept this one out of sprint/commitment (has depencency on audit that didn't take place in this sprint)
Story Points done |  | 24
Story Points left: |  | 0
Sprint Backlog
Things (8) | Type | Story Points (24) | Description
id-1 | story | 3 | As a patient, I want to register.
id-2 | story | 3 | As a patient, I want to login.
id-3 | story | 3 | As a patient, I want the site to remember my password.
id-4 | story | 3 | As a patient, I want to logout.
id-5 | story | 3 | As a doctor, I want to register.
id-6 | story | 3 | As a doctor, I want to login.
id-7 | story | 3 | As a doctor, I want the site to remember my password.
id-8 | story | 3 | As a doctor, I want to logout.

## Sprint 2
Sprint 2
Name |  | Main sprint |  |  |  | 0
Goal |  | add main functionality |  | Duration | 10 working days
Process improvement |  | improve sprint planning |  | Things | 11 things
Start Date |  | 2025-08-09 |  | Story Points | 41 points
End Date |  | 2025-08-22 |  |  |  | days left
Sprint Metrics
Things Planned |  | 12 | Key Achievements | Key Achievements Completed 12 user stories (44 story points) focused on advanced doctor–patient interactions (patient management, report upload/delete, profile visualization, messaging). Implemented end-to-end workflow for analysis reports: upload → share with patient → patient visualization. Introduced patient–doctor communication via chat for clarifications on reports. Process Improvements Process improvement from previous sprint achieved: clearer separation between patient and doctor responsibilities in backlog refinement. Process improvement from current sprint partly achieved: started adoption of report management automation, but full integration with patient notification still pending.
Points Planned |  | 44
Things done: |  | 12
Things left: |  | 0 | Performance Summary | IMTA-2557 we should have kept this one out of sprint/commitment (has depencency on audit that didn't take place in this sprint)
Story Points done |  | 44
Story Points left: |  | 0
Sprint Backlog
Things (12) | Type | Story Points (44) | Description
id-9 | story | 3 | As a doctor, I want to add patients to my list of patients.
id-10 | story | 3 | As a doctor, I want to remove patients to my list of patients.
id-11 | story | 3 | As a doctor, I want to search patients.
id-12 | story | 6 | As a doctor, I want to see the entire medical profile of my patients.
id-13 | story | 4 | As a doctor, I want to upload the analysis reports of my patients.
id-14 | story | 3 | As a doctor, I want to delete my reports.
id-15 | story | 5 | As a doctor, I want to share the analysis reports with the patients, with explanation.
id-16 | story | 3 | As a doctor, I want to filter my reports by sector.
id-17 | story | 3 | As a patient, I want to visualize the analysis reports shared by the doctor.
id-18 | story | 3 | As a doctor, I want to have contact of patients along with reports.
id-19 | story | 5 | As a patient, I want to be notified by the doctor if he sees bad things in reports.
id-20 | story | 3 | As a doctor, I want to send messages to my patients through a chat in case of further explanation.

## Sprint 3
Sprint 3
Name |  | Details sprint |  |  |  | 0
Goal |  | add more awesome functionality |  | Duration | 10 working days
Process improvement |  | improve sprint planning |  | Things | 13 things
Start Date |  | 2025-08-23 |  | Story Points | 49 points
End Date |  | 2025-09-05 |  |  |  | days left
Sprint Metrics
Things Planned |  | 14 | Key Achievements | Key Achievements Completed 14 user stories (50 story points) focused on reminders, notifications, and doctor–patient communication. Delivered full reminder management: set, edit, remove, and timeline visualization with notification history. Enabled multi-doctor collaboration through chat and email to improve patient case comparisons. Added patient features for exporting reports as PDF and managing contact/notification preferences. Process Improvements Process improvement from previous sprint achieved: better handling of dependencies between messaging and notification features during backlog refinement. Process improvement from current sprint partly achieved: initial integration of notification preferences with profile management, pending full rollout of cross-channel alerts.
Points Planned |  | 52
Things done: |  | 14
Things left: |  | 0 | Performance Summary | IMTA-2557 we should have kept this one out of sprint/commitment (has depencency on audit that didn't take place in this sprint)
Story Points done |  | 52
Story Points left: |  | 0
Sprint Backlog
Things (14) | Type | Story Points (52) | Description
id-21 | story | 3 | As a patient, I want to send messages to my doctors through a chat in case of explanation, after the doctor has contacted me.
id-22 | story | 4 | As a doctor, I want to contact other doctors of my patients via email.
id-23 | story | 3 | As a doctor, I want to have contact of other doctors of my patients for a further comparison.
id-24 | story | 3 | As a doctor, I want to send messages to other doctors of my patients through a chat.
id-25 | story | 3 | As a doctor, I want to access analysis reports of other sectors.
id-26 | story | 5 | As a patient, I want to be notified when it's time to get new analysis.
id-27 | story | 4 | As a doctor, I want to set the reminder cadence per test type.
id-28 | story | 3 | As a doctor, I want to edit the reminder.
id-29 | story | 4 | As a patient, I want to see a timeline with upcoming reminders and notification history.
id-30 | story | 4 | As a patient, I want to manage my contact info & notification preferences from profile.
id-31 | story | 5 | As a patient, I want to export my reports as PDF.
id-32 | story | 3 | As a doctor, I want to remove a reminder.
id-33 | story | 4 | As a patient, I want to be able to open the report file.
id-34 | story | 4 | As a patient, I want to reply to the report once received.

## Velocity
Velocity | Sprint | Sprint 1 | Sprint 2 | Sprint 3
11.3333 | Planned Things | 8 | 12 | 14
40 | Planned Points | 24 | 44 | 52
11.3333 | Finished Things | 8 | 12 | 14
40 | Finished Points | 24 | 44 | 52
1.5967 | Points per dev day | 1.6 | 1.46 | 1.73
100% | Commit Score | 100% | 100% | 100%